PROPOSAL

TO:		Shannon Hayden, National Research Center, Inc. (NRC)

FROM:		Clark Arneson, City Manager

DATE:		February 23, 2012

RE:		Proposal for Resident Survey

Summary of Need

The city of Blaine desires to contract with NRC to assist in its planning process and obtain reliable feedback about city issues and plans from residents within the City.

Proposed Services

NRC proposes to provide the City of Blaine with a scientific, random sampled, mailed survey drawn from a source list provided by the United States Postal Service for residents within the City of Blaine boundaries. The structure of the survey will include approximately 5 pages of survey questions, including any open ended questions, with a proposed mailing size of 1,200 households (likely to yield 300-480 completed surveys with a margin of error at the 95% confidence level of +/- 4.5 to 5.7 %).

Services will include telephone meetings with staff on the survey design and results, three contacts with each household (a pre-notification, survey, and reminder), data analysis with comparisons, key driver analysis and benchmarking, a final report with executive summary and in-person final presentation to our City Council.

Project Cost

The cost of the five (5) page survey, with a mailing size of 1,200 and an estimated 300-480 completed surveys, including design, implementation, analysis and final report is $18,920. Should the City choose to include more pages of the survey or additional reminder postcards, NRC will provide a revised cost estimate before proceeding.

Time Line

The following dates will be used as the initial time line for the Residential Survey. Should issues arise or minor date changes need to be made, NRC will consult with the City Manager and/or his designee to adjust them accordingly. It is the understanding of the City of Blaine and NRC that the goal is to have the draft full report submitted to the City of Blaine by mid-late May 2012, if permitted by the timing of the survey mailings.

Activity	Date

Contract execution and formal project initiation	February

Develop survey instrument and mailing materials (iterative process)	through March 16

Mail prenotification postcard	March 21

Mail first wave of surveys	March 27

Mail second wave of surveys	April 2

Data collection	through May 1

Electronic data entry	through May 4

Data analysis and report writing	through May 21

Draft report emailed for review	May 21

City review of draft	through May 28

Final report emailed	June 4

Presentation to Council	TBD

Approval

The signatures below constitute approval of the summary proposal as outlined above and in the original Request for Proposal submitted by National Research Center, Inc. dated December 5, 2011.

_______________________________		__________________________________

On Behalf of the City of Blaine			Date

Tom Ryan, Mayor

_______________________________		___________________________________

On Behalf of the City of Blaine			Date

Clark Arneson, City Manager

________________________________		___________________________________

On Behalf of National Research Center, Inc.		Date