FEASIBILITY REPORT

11-11 - TABLE OF CONTENTS
FEASIBILITY REPORT

EXECUTIVE SUMMARY
FR-1

1. PROJECT HISTORY
FR-2

2. PROJECT AREA CHARACTERISTICS
FR-2

3. PROPOSED IMPROVEMENTS
FR-2

A.  Sanitary Sewer
FR-3
B.  Water Main
FR-3
C.  Street Construction
FR-3
D.  Storm Drainage
FR-4
4. IMPACT OF PROPOSED IMPROVEMENTS
FR-4
5. SUMMARY OF ESTIMATED PROJECT COSTS AND FUNDING
FR-5
6. ASSESSMENT METHODOLOGY
FR-6
7. FINANCE
FR-6
A.  Finance Director Statement
FR-6
8. PROJECTED SCHEDULE
FR-7
9. PROJECT FEASIBILITY AND RECOMMENDATION
FR-7
EXHIBITS

1.  Project Location

2.  Sanitary Sewer Location Map
3.  Water Main Location Map 
4.  Proposed Street and Storm Sewer Location Map
5.  Assessable Parcels

6.  Proposed Assessment Roll 
	
	

	
	


EXECUTIVE SUMMARY
The proposed project will partially reconstruct Davenport Street NE from 99th Lane NE to 105th Avenue NE.  Proposed improvements include the construction of right turn lanes at 104th Avenue NE, 103rd Avenue NE, and entrance to National Sports Center, a realignment of the intersection of 99th Lane NE and Davenport Street NE, total concrete curb and gutter replacement, spot concrete sidewalk replacement, new concrete sidewalk, storm sewer structures, asphalt surface, traffic control signage, signal modification, striping, and appurtenant construction. 
The estimated cost of improvements is $1,148,200 with $499,000 proposed to be assessed over a ten-year period.  Replacement of existing sanitary sewer castings/rings and relocation of hydrants, estimated cost of $23,220 is proposed to be paid for by the City Public Utility Fund.  The remaining portion of $625,980 is proposed to be paid from the City’s Municipal State Aid Street funds and the City’s Pavement Management Program Funds.  
The project is necessary, cost-effective, and feasible and will result in a benefit to the properties proposed to be assessed.

1. PROJECT HISTORY
The Blaine City Council initiated the project and ordered the preparation of a feasibility report on September 15, 2011, with Resolution No. 11-0116.
This report is based on field observations, record drawing information, 2010 aerial photography, and 2011 topographic survey.

2. PROJECT AREA CHARACTERISTICS
The project area includes Davenport Street NE, beginning at 99th Lane NE and terminating at 105th Avenue NE (CR87).  
The existing segment of Davenport Street NE from 99th Lane NE to 101st Avenue NE was constructed in 1980 as 40 foot wide paved urban section with storm sewer, sanitary sewer, and water main.  The segment of Davenport Street NE from 101st Avenue NE to 105th Avenue NE was constructed in 1989 as a 37.5 to 42 foot wide paved urban section with storm sewer, sanitary sewer, and water main.  There is an existing six foot concrete sidewalk on the west side of Davenport Street NE from 105th Avenue NE extending south to 103rd Avenue NE.  Both street segments received a pavement preservation treatment of a seal coat in 1995.     
The Anoka County Soil Survey indicates the predominant soil types in the project area to be Lacustrine sand with silt.  Based on past projects in the area, the project will require dewatering operations to install underground improvements.  
The proposed project is located in the Coon Creek Watershed District.  Davenport Street NE drains to County Ditch 41 (Sand Creek) which is part of the Federal Emergency Management Agency designated flood area.  As the project is not proposing to change the elevation of these roadways there will be no issue with the flood plain mitigation.   No portion of the project will impact wetlands as identified on the City’s wetland inventory map. 
See Exhibit No. 1 for the project location.

3. PROPOSED IMPROVEMENTS
The proposed improvements will include partial reconstruction of the existing urban street section, modifying the existing storm drainage system, relocation of hydrants, and replacement of sanitary sewer castings and rings, construction of three right turn lanes, realign the intersection of 99th Lane NE and Davenport Street NE, and modifications to the existing signal at 105th Avenue NE.  The improvements are necessary, cost-effective, and feasible.  Each improvement is further described as follows:

A.
Sanitary Sewer
Public Works and Engineering staffs have reviewed the existing sanitary sewer along the Davenport Street NE corridor and concur that there are no issues with the existing mains.  The project will include the removal of the existing manhole castings/rings and installation of new castings/rings on all sanitary manholes.  
See Exhibit No. 2 for the sanitary sewer location map.
B.
Water Main
Public Works and Engineering staffs have also reviewed the water main installation dates and water main break data along the Davenport Street NE corridor and concur that there are no issues with the existing main.  Therefore, the scope of the project will not include any replacement of existing water main along the corridor.  The project will include relocation of several existing hydrants and hydrant gate valves, along with adjusting existing gate valve boxes located within the street typical sections.  

See Exhibit No. 3 for the water main location map.


C.
Street Construction
The proposed construction will begin at the southerly terminus of 99th Lane NE and continue northerly over the existing Davenport Street NE alignment terminating at 105th Avenue NE.  The proposed project will partially reconstruct the existing typical section. The street typical section will be reconstructed with a section composed of 6 -inches bituminous on 8-inches of reclaimed gravel base over a compacted subgrade.  A field survey of the existing curb shows that over 50% needs to be replaced.  The project will propose full reconstruction of the existing curb.
The proposed project will remove and update all pedestrian ramps and crossings to current ADA standards along with any broken sidewalk panels.  The project also proposes to install a segment of sidewalk on the east side of Davenport from the main entrance into the National Sports Center north to 105th Avenue.
The preliminary survey by E.G. Rud and Sons indicates dedicated right-of-way at 80 feet on Davenport Street NE.  Please note that the existing street section was not constructed centered within the right of way.  As such, additional Right-of-Way will be required from the National Sports Center to construct the proposed right turn lane and a trail easement for the proposed sidewalk/trail.  
See Exhibit No. 4 for the proposed street and storm sewer location map.

D.
Storm Drainage
Storm water runoff from the streets will be captured and controlled with the existing catch basins and storm sewer pipe system.  The project is proposing to replace all existing brick storm sewer structures with precast structures and convert several to sump structures to aid in the removal of sediments.  The project will include the removal of the existing castings and rings and installation of new castings and rings on all storm sewer structures.  It is anticipated that several infiltration practices will need to be incorporated to the existing storm sewer system to meet the watershed requirements.   

Coon Creek Watershed District will conduct a plan review for the project.   
See Exhibit No. 4 for the proposed street and storm sewer location map.

4. IMPACT OF PROPOSED IMPROVEMENTS
The proposed street improvements will not create any new maintenance issues for the Public Works staff other than the annual cleaning of the sump manholes.  The City will work with affected property owners and the Contractor to resolve any situation that may arise during construction.  Short term traffic delays, construction dust and noise, and erosion will occur.  Efforts to minimize these impacts include the restriction of work hours and dust and erosion control measures included in the project.  Any disruptions that occur to existing yards, sprinkler systems, and driveways will be restored.
SUMMARY OF ESTIMATED PROJECT COSTS AND FUNDING
Project:
11-11
Description:
Davenport Street NE Improvements
	Cost Item
	Percent
	Amount

	
	
	
	

	Construction Costs
	
	
	
	
	

	
Street Construction

Storm Sewer

Water Main


Sanitary Sewer
	
	$
	789,570
43,780
9,050
8,150
	
	

	
Total Construction Costs
	
	
	
	$
	850,550

	
	
	
	
	
	

	Administrative Costs
	
	
	
	
	

	
Engineering


Assessment


Legal


Administration


Capitalized Interest


Bonding
	18%

 1%

  2%

  4%

  8%

  2%
	$
	153,100
8,500
17,000
34,020
68,030
17,000
	
	

	
Total Administrative Costs
	
	
	
	$
	297,650

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	TOTAL ESTIMATED PROJECT COSTS
	
	
	
	$
	1,148,200

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	
	
	
	

	
	
	
	

	Temporary Funding Source
	City Internal Funds

	Permanent Funding Source
	MSAS Funds, Assessments, Pavement Management Program Funds (PMP Funds), and Public Utility Funds,

	(ENR Construction Index for November 2011 is 10271.36)

	
	
	
	

	Funding
	
	
	

	Total Paid from Public Utility Funds
	$ 23,220

	Total Generation from Assessments
	$ 499,000 

	Total Paid from MSAS Fund/PMP Funds
	$ 625,980


 6.
ASSESSMENT METHODOLOGY
It is proposed that the project be assessed over 10 years in accordance with the City’s Assessment Policy.  It is proposed to assess this project using the linear footage method for the commercially zoned parcels.  The front foot assessments are based on 50% of the entire cost of the improved street section per the city assessment policy.    
See Exhibit No. 5 for the parcels proposed to be assessed and Exhibit No. 6 for the proposed assessment roll.   
7.
FINANCE
The proposed project will be temporarily financed by the City.  Permanent funding will be provided by the MSAS account, MSAS Street Maintenance account, Pavement Management Program Funds, city water and sewer utility funds, and the costs assessed to the benefiting parcels in accordance with current City Assessment Policy and Minnesota Statutes Chapter 429, Special Assessment Laws.

A.
Finance Director Statement
With reference to this Feasibility Report for Improvement Project 11-11 as prepared by the City of Blaine Engineering Department dated January 19, 2012, I find the following:

1. The project will be temporarily funded through existing City internal funds whereupon permanent financing will be obtained through the City’s Municipal State Aid Street Funds, MSAS Street Maintenance Funds, Pavement Management Program Funds, Public Utility Funds, and assessments.
2. Sufficient moneys are currently available from the City’s internal funds to temporarily fund the special assessment portion of the project.  It is estimated that $499,000 will be assessed.

3. Sufficient moneys are currently available from the City’s Public Utility Funds to pay for proposed utility improvements for street reconstruction at an estimated cost of $23,220.




Joseph Huss, Finance Director
8.
PROJECTED SCHEDULE

January 19, 2012
Receive Feasibility Report


Order Public Hearing
February 14, 2012
Public/Business Information Meeting to discuss project and proposed assessments

February 16, 2012
Hold Public Hearing
Order Improvements and Order Preparation of Plans and Specifications

April 5, 2012

Approve Plans and Specifications




Order Advertisement for Bids

May 8, 2012

Open Bids

May 17, 2012
Award Contract

Aug – Oct 2012
Construct Improvements

November 2012
Assess Project

2013


First assessment payment due with real estate taxes

9.
PROJECT FEASIBILITY AND RECOMMENDATION
The project as proposed is technically and financially feasible, cost effective, and will result in a benefit to the properties proposed to be assessed.  It is recommended that the Council accept this report, hold the public hearing, and order the improvements.
	City of Blaine - Feasibility Report
	FRTOC-1


PAGE  
FR-7
City of Blaine - Feasibility Report

H:\TEAM\GISENG\PUBLIC PROJECTS\2011 PROJECT LIST\11-11 DAVENPORT\FEASIBILITY REPORT\REPORT.DOC

