EXECUTIVE SUMMARY	FR-1

- PROJECT HISTORY	FR-2

- PROJECT AREA CHARACTERISTICS	FR-2

- PROPOSED IMPROVEMENTS	FR-2

- A.  Sanitary Sewer	FR-3

- B.  Water Main	FR-3

- C.  Street Construction	FR-3

- D.  Storm Drainage	FR-4

- IMPACT OF PROPOSED IMPROVEMENTS	FR-4

- SUMMARY OF ESTIMATED PROJECT COSTS AND FUNDING	FR-5

- ASSESSMENT METHODOLOGY	FR-6

- FINANCE	FR-6

- A.  Finance Director Statement	FR-6

- PROJECTED SCHEDULE	FR-7

- PROJECT FEASIBILITY AND RECOMMENDATION	FR-7

- EXHIBITS

- 1.  Project Location

- 2.  Sanitary Sewer Location Map

- 3.  Water Main Location Map

- 4.  Proposed Street and Storm Sewer Location Map

- 5.  Assessable Parcels

- 6.  Proposed Assessment Roll

EXECUTIVE SUMMARY

- The proposed project will partially reconstruct Oak Park Boulevard NE and 119th Avenue NE from 125th Avenue NE to Jefferson Street NE.  Proposed improvements include spot concrete curb and gutter replacement, spot concrete sidewalk replacement, storm sewer structures, asphalt surface, traffic control signage, striping, and appurtenant construction.

- The estimated cost of improvements is $1,393,200 with $145,590 proposed to be assessed over a ten-year period.  Replacement of existing hydrants, existing sanitary sewer drop structures and castings/rings, estimated cost of $94,500 is proposed to be paid for by the City Public Utility Fund.  The remaining portion of $1,153,110 is proposed to be paid from the City’s Municipal State Aid Street funds and the City’s Pavement Management Program Funds.

- The project is necessary, cost-effective, and feasible and will result in a benefit to the properties proposed to be assessed.

- PROJECT HISTORY

- The Blaine City Council initiated the project and ordered the preparation of a feasibility report on September 15, 2011, with Resolution No. 11-0117.

- This report is based on field observations, record drawing information, 2010 aerial photography, and 2011 topographic survey.

- PROJECT AREA CHARACTERISTICS

- The project area includes Oak Park Boulevard NE/119th Avenue NE, beginning at 125th Avenue NE and terminating at Jefferson Street NE.

- The existing Oak Park Boulevard NE and 119th Avenue NE were constructed in 1970.  These two street segments were constructed as 44 foot paved urban sections with storm sewer, sanitary sewer, and water main.  There is existing five foot concrete sidewalk on both sides of Oak Park Boulevard NE.  The walk on the west side begins at 125th Avenue NE and extends south to 122nd Avenue NE where it transitions into a bituminous trail and extends west into Northwood Park.  The walk on the east side begins at 125th Avenue NE and extends south to 121st Avenue NE, where it transitions into a bituminous trail that extends east into the Baseball Complex Park.  Both street segments have received previous pavement preservation treatments including a bituminous overlay in 1992 and seal coat in 2000.

- The Anoka County Soil Survey indicates the predominant soil types in the project area to be Lacustrine sand with silt.  Based on past projects in the area, the project will require dewatering operations to install underground improvements.

- The proposed project is located in the Coon Creek Watershed District.  Oak Park Boulevard crosses over County Ditch 60-Branch 2 which is part of the Federal Emergency Management Agency designated flood area.  As the project is not proposing to change the elevation of these roadways there will be no issue with the flood plain mitigation.   No portion of the project will impact wetlands as identified on the City’s wetland inventory map.

- See Exhibit No. 1 for the project location.

- PROPOSED IMPROVEMENTS

The proposed improvements will include partial reconstruction of the existing urban street section, modifying the existing storm drainage system, replacement of hydrants, and replacement of sanitary sewer castings and rings.  The improvements are necessary, cost-effective, and feasible.  Each improvement is further described as follows:

- A.	Sanitary Sewer

- Public Works and Engineering staffs have reviewed the existing sanitary sewer along the Oak Park Boulevard NE and 119th Avenue NE corridor and concur that there are no issues with the existing mains.  The project will include the removal of the existing manhole castings/rings and installation of new castings/rings on all sanitary manholes.  The project also proposes to reconstruct several drop manhole connections to correct potential long term maintenance issues.

- See Exhibit No. 2 for the sanitary sewer location map.

- B.	Water Main

- Public Works and Engineering staffs have also reviewed the water main installation dates and water main break data along the Oak Park Boulevard NE and 119th Avenue NE corridor and concur that there are no issues with the existing main.  Therefore, the scope of the project will not include any replacement of existing water main along the corridor.  The project will include removal and replacement of the existing hydrants and hydrant gate valves along with adjusting existing gate valve boxes located within the street typical sections.

- See Exhibit No. 3 for the water main location map.

- C.	Street Construction

- The proposed construction will begin at the southerly terminus of Jefferson Street NE and continue easterly over the existing 119th Avenue  NE alignment and then northerly over the existing Oak Park Boulevard NE alignment, terminating at 125th Avenue NE.  The proposed project will partially reconstruct the existing typical section. The street typical section will be reconstructed with a section composed of 4 -inches bituminous on 8-inches of reclaimed gravel base over a compacted subgrade.  Partial reconstruction of the existing curb is proposed with approximately 30% removed and replaced.

- The proposed project will remove and update all pedestrian ramps and crossings to current ADA standards along with any broken sidewalk panels.

- The preliminary survey by E.G. Rud and Sons indicates dedicated right-of-way varies from 66 feet to 205 feet on Oak Park Boulevard NE and 66 feet on 119th Avenue NE.  There is no anticipated additional right-of-way needed for the project.

- See Exhibit No. 4 for the proposed street and storm sewer location map.

- D.	Storm Drainage

- Storm water runoff from the streets will be captured and controlled with the existing catch basins and storm sewer pipe system.  The project is proposing to remove all existing block constructed storm sewer structures and reconstruct all to precast structures also converting several to sump structures to aid in the removal of sediments.  The project will include the removal of the existing castings and rings and installation of new castings and rings on all storm sewer structures.

- Coon Creek Watershed District will conduct a plan review for the project.

- See Exhibit No. 4 for the proposed street and storm sewer location map.

- IMPACT OF PROPOSED IMPROVEMENTS

The proposed street improvements will not create any new maintenance issues for the Public Works staff other than the annual cleaning of the sump manholes.  The City will work with affected property owners and the Contractor to resolve any situation that may arise during construction.  Short term traffic delays, construction dust and noise, and erosion will occur.  Efforts to minimize these impacts include the restriction of work hours and dust and erosion control measures included in the project.  Any disruptions that occur to existing yards, sprinkler systems, and driveways will be restored.

SUMMARY OF ESTIMATED PROJECT COSTS AND FUNDING

- Project:	11-12

- Description:	Oak Park Boulevard NE/119th Avenue NE Improvements

| # Cost Item | Percent | Amount |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Construction Costs |  |  |  |  |  |  |
| Street Construction Storm Sewer Water Main Sanitary Sewer |  | $ | 849,335 112,665 41,700 28,300 |  |  |  |
| Total Construction Costs |  |  |  |  | $ | 1,032,000 |
| Administrative Costs |  |  |  |  |  |  |
| Engineering Assessment Legal Administration Capitalized Interest Bonding | 18% 1% 2% 4% 8% 2% | $ | 185,760 10,320 20,640 41,280 82,560 20,640 |  |  |  |
| Total Administrative Costs |  |  |  |  | $ | 361,200 |
| TOTAL ESTIMATED PROJECT COSTS |  |  |  |  | $ | 1,393,200 |
| Temporary Funding Source | City Internal Funds |  |  |  |  |  |
| Permanent Funding Source | MSAS Funds, Assessments, Pavement Management Program Funds (PMP Funds), and Public Utility Funds, |  |  |  |  |  |
| (ENR Construction Index for November 2011 is 10271.36) |  |  |  |  |  |  |
| Funding |  |  |  |  |  |  |
| Total Paid from Public Utility Funds | $ 94,500 |  |  |  |  |  |
| Total Generation from Assessments | $ 145,590 |  |  |  |  |  |
| Total Paid from MSAS Fund/PMP Funds | $ 1,153,110 |  |  |  |  |  |

6.	ASSESSMENT METHODOLOGY

- It is proposed that the project be assessed over 10 years in accordance with the City’s Assessment Policy.  It is proposed to assess this project using the unit method for the residential properties.  This method was chosen over the linear foot method due to the equal benefit per lot along the project corridor.  The unit method helps to more equitably spread the costs of the project between small lots to larger lots, with neither receiving more benefit from the project.  Commercially zoned parcels are proposed to be assessed per linear foot.  Proposed unit assessments are based on 25% of the entire cost of an equivalent 29 foot residential street improvement and the front foot assessments are based on 50% of the entire cost of the improved 44 foot commercial street section per the city assessment policy.

- See Exhibit No. 5 for the parcels proposed to be assessed and Exhibit No. 6 for the proposed assessment roll.

- 7.	FINANCE

The proposed project will be temporarily financed by the City.  Permanent funding will be provided by the MSAS account, MSAS Street Maintenance account, Pavement Management Program Funds, city water and sewer utility funds, and the costs assessed to the benefiting parcels in accordance with current City Assessment Policy and Minnesota Statutes Chapter 429, Special Assessment Laws.

- A.	Finance Director Statement

With reference to this Feasibility Report for Improvement Project 11-12 as prepared by the City of Blaine Engineering Department dated January 19, 2012, I find the following:

      - The project will be temporarily funded through existing City internal funds whereupon permanent financing will be obtained through the City’s Municipal State Aid Street Funds, MSAS Street Maintenance Funds, Pavement Management Program Funds, Public Utility Funds, and assessments.

      - Sufficient moneys are currently available from the City’s internal funds to temporarily fund the special assessment portion of the project.  It is estimated that $145,590 will be assessed.

      - Sufficient moneys are currently available from the City’s Public Utility Funds to pay for proposed utility improvements for street reconstruction at an estimated cost of $94,500.

- Joseph Huss, Finance Director

- 8.	PROJECTED SCHEDULE

- January 19, 2012	Receive Feasibility Report

- Order Public Hearing

- February 14, 2012	Public/Business Information Meeting to discuss project and proposed assessments

- February 16, 2012	Hold Public Hearing

- Order Improvements and Order Preparation of Plans and Specifications

April 5, 2012		Approve Plans and Specifications

Order Advertisement for Bids

- May 8, 2012		Open Bids

- May 17, 2012	Award Contract

- June – Sept 2012	Construct Improvements

- October 2012	Assess Project

- 2013			First assessment payment due with real estate taxes

- 9.	PROJECT FEASIBILITY AND RECOMMENDATION

- The project as proposed is technically and financially feasible, cost effective, and will result in a benefit to the properties proposed to be assessed.  It is recommended that the Council accept this report, hold the public hearing, and order the improvements.